## Slide 1: MOLLER Spectrometer – WBS 1.03
MOLLER Collaboration Meeting
June 21-22, 2022
Michael Bevins
Level 2 CAM (Interim)
Jefferson Lab

## Slide 2: Outline
Spectrometer Team
Scope Overview
Technical Reviews
Schedule Snapshot
Status

## Slide 3: Spectrometer Team
  JLab Key Support Team
    Mike Beck – S&A, Eng Division
    Ryan Biraben – Hall A Phy, Division
    Kris Cleveland – ME Grp, Eng Division
    Chuck Hutton – ME Grp, Eng Division
    Onish Kumar - DC Power, Eng Division
    Joe Lamont – ME Grp, Eng Division
    Joe Meyer – S&A, Eng Division
    Sarin Philip – DC Power, Eng Division
    Nick Sandoval – Hall D, Phy Division
    Scot Spiegel – Hall D, Phy Division
    Cameron Sutton – ME Grp, Eng Division
    Randy Wilson - Magnet Group, Phy Division
    Dan Young – Magnet Group, Phy Division
  MIT Upstream Torus Key Support Team
    James Kelsey
    Jason Bessuille
    Ernie Ihloff
    Danielle Petterson
  L2 Manager, Control Account Manager
    Michael Bevins (Interim), ME Grp, Eng Division
  L2 Technical Leads
    Dave Kashy (Engineering), Magnet Group, Phy Division
    Juliette Mammei (Physics), U. of Manitoba
    Robin Wines (System Interfaces), Hall A Phy, Division
  L3 Technical Leads
    Coils, coil support system, Assembly, water chiller, vacuum pumping system
      Dave Kashy, Magnet Group, Phy Division
    Collimators, beam pipes,, magnet enclosures, windows
      Sandesh Gopinath, Magnet Group, Phy Division
      Eric Sun, Magnet Group, Phy Division
    Power supplies, instrumentation and control, field measurement system
      Probir Ghoshal, Magnet Group, Phy Division

## Slide 4: Scope Overview
Downstream Torus System
(Focusing and separation of particles)
Upstream Torus System
(Pre-bending of particles)
Hybrid Lead Wall
Detector Pipe & Pion Donut Support
Drift Pipe, Window & Shutter
Spectrometer Scope
~30 meters
Interface to Target Chamber
Interface to Dump Tunnel Beampipe
Beam Direction

## Slide 5: Technical Reviews Held
  Sub-System Preliminary Design Reviews:
    Downstream Toroid Coils – March 2021
    Magnet Power Supplies, Current Leads and Jumpers – April 2021
    Beam Pipes, Bellows and Windows – July 2021
  Full Spectrometer System Preliminary Design Review – May 2022

## Slide 6: Schedule Snapshot
  Key Dates: (L3 Milestones)
    Spectrometer FDR 17-Nov-2022
    CD2/3 IPR
    16-Feb-2023

## Slide 7: Status – Design & Prototyping
Upstream Torus
  Good progress… particularly with the collimator 1 and enclosure design. Coil design in place. Still working coil supports
Downstream Torus
  Coil support design well advanced and detail drawings produced for prototype support procurement
  Enclosure
    3D model and detailed engineering analysis complete
  Prototype Coils
    Conductor received, coil winding at vendor underway
Magnet Power Supplies & I&C
  Prototype power supply contract awarded, vendor effort well underway
  Magnet safety and interlocks identified
Beam Pipes, Bellows, & Window
  Prototype window drawings complete. Vendor quote received – award imminent
  Bellows specification developed. Vendor quote received for all bellows. Planning to prototype one bellows to qualify vendor
Pion Donut/Detector Pipe Support
  Preliminary design and engineering analysis complete
Downstream Torus Prototype Coil Winding & Test Power Supply