## Slide 1: MOLLER Collaboration Meeting
Beamlines and Bellows
Eric Sun
On behalf of MOLLER Team
May 5-6, 2023

## Slide 2: Outline
Overview
Status Summary
Beam Pipes and Supports
  Drift Pipe
  Detector Pipe and Support
Windows
  Prototype Window and Detector Window
Bellows
  Bellows 1, 2, 3, 4, 5, and 7
Conclusion

## Slide 3: Overview
12’’ bellows 1
12’’ bellows 2
26’’ bellows 3
54’’ bellows 4
41’’ bellows 5
16’’ bellows 7
12’’ beam pipe
Collar 0
US enclosure
DS enclosure
Drift pipe
Detector pipe
SAM pipe
OD = 96.5’’
OD = 54.76’’
OD = 100’’
Detector window
Neckdown window
Support of dump entry pipe

## Slide 4: Status Summary
Component | CD-3a | Drawings | RFI | SOW | Note
Drift Pipe | Yes | Approved | Yes | 75% done | 
Detector Pipe | Yes | Approved | Yes | 75% done | 
Neckdown Window | Yes | Approved | Yes | 75% done | 
Bellows 1-5 | Yes | Approved | Yes | 90% done | 
Bellows 7 | Yes | Approved | Yes | NA | Received, tested, accepted
Detector Pipe and pion donut Support | Yes | Draft drawings complete | Yes |  | 
Prototype Window | No | Approved | Complete | NA | Pressure-tested
Support of Beam Dump Entry Pipe | No | Approved | No |  | 
SAM Pipe | No | Reviewed and updated | No |  | 
Beam Pipe from Target to Collar 0 | No | Reviewed and updated | No |  | 
Detector Window | No | Ready for signatures | No |  | 
Shutter of Detector Window | No | Reviewed and updated | No |  | 

## Slide 5: Drift Pipe
Shutter Frame
Drift pipe support
Drift pipe
8’’ vacuum line
Bellows 4
Parallel plate
7/8’’ thick
OD = 100’’
Pump
Drift pipe was designed per ASME Section VIII Division 1.
Division 2 was used to cross-check the results.
Thickness = 7/8’’
  Pmax_allow._ext (Div 1) = 26.8 psi > 14.7 psi
  Pmax_allow._ext (Div 2) = 29.5 psi
There are 4 vertical (Y) links, 2 X links and one Z link to support the drift pipe.
Under gravity and vacuum, motions are
  X of US, DS flange = 0.02 mm, 0.1 mm
  Y of US, DS flange = 0.09 mm, 0.6 mm
  Z of US, DS flange = 0.7 mm, 0.9 mm
Status
  All drawings (except drawings of bottom support) were approved.
Atmospheric pressure = 14.7 psi
X
Y
Z
Beam direction
Al 6061-T6

## Slide 6: Detector Pipe and Pion Donut Support Assembly
Detector Pipe
Designed per ASME Section VIII Division 1. Division 2 was used to cross-check the result.
  Pmax_allow._ext (Div 1) (0.75’’) = 53.7 psi >> 14.7 psi
  Pmax_allow._ext (Div 1) (0.25’’) = 30.9 psi >> 14.7 psi
All drawings were approved.
Detector Pipe Support
Radial deflection at US end of detector pipe < 3 mm when vacuum is applied;
Draft drawings of the Pion Donut canning, the Frame, the Tube Assy, Fins, and Supports are complete;
All draft drawings will be reviewed as a package next week.
Detector pipe
Tube assy
Pion donut
Wall mount supports
Vertical support
Axial support
Vertical support
Fins
Stiffening ring
Thickness = 0.25’’
Thickness = 0.75’’

## Slide 7: Prototype Window and Detector Window
Prototype Window
  Same material (Al 5083-H116) as Detector Window, same thickness in thinned regions to test machining;
  Pressure tested on 12-20-2022; test pressure = 0-5-0 psi (fixed a leak on a threaded fitting); 0-5-10-15-0 psi; 0-22-27.8-0 psi;
  Max z motion = 0.056 in (22 psi), 0.069 in (27.8 psi), 0.002 in (0 psi);
  No plastic deformation up to 27.8 psi;
  Plan to test to higher pressure in 2023.
Detector Window
  Drawings are reviewed and ready for signature
MOLLER Collaboration Meeting
Test Assembly of Prototype Window
Welded Prototype
Gauge at 22 psi
Detector window

## Slide 8: Bellows
Bellows | Material | Seal Type | Flange Thick (in) | Free Length (in) | Axial Spring Rate | Lateral Spring Rate | Angular Spring Rate | Axial Range (in) | Lateral offset (in) | Angular offset () | Required Cycles*
1&2 | SS 316L | CF - Al | 1.125 | 18 | 1250 | 5000 | 600 | 1.5 | 0.5 | 3 | 20
3 | SS 316L | O-ring | 0.6 | 24 | 1000 | 5000 | 2000 | 2.5 | 0.5 | 3 | 20
4 | SS 316L | O-ring | 0.6 | 15.75 | 1200 | 25000 | 8000 | 1.25 | 0.3 | 3 | 20
5 | Inconel | O-ring | 0.6 | 24.5 | 800 | 4000 | 2500 | 1.25 | 0.5 | 3 | 20
7 | Inconel | CF - Al | 1.12 | 20.56 (22.0) | 600 | 1000 | 250 | 0.75 | 0.5 | 3 | 20
O-ring material is peroxide-cured EPDM; Al gasket is Al 1100-O.
Unit for axial spring rate and lateral spring rate is lbf/in; unit for angular spring rate: lbf-in/deg.
E310/ER310 welding rods will be used to weld bellows 1-4.
Status: All drawings were approved.
Bellows 7 procured and tested – ready to install!
12’’ SS Bellows 1
12’’ SS Bellows 2
26’’ SS Bellows 3
54’’ SS Bellows 4
41’’ Inconel 625 Bellows 5
18’’ Inconel 625 Bellows 7
* At max deflections (only needed during some installations).

## Slide 9: Acceptance Tests of Bellows 7
Welding quality is excellent.
Leak test confirms that Bellows 7 meets JLab’s specification.
Dimensional inspection indicates free length of Bellows 7 is 20.56’’ (B), short by 1.44’’. SAM pipe was extended 1.44’’.
Permeability measurements found that company name plate was not Inconel 625. Removed.
Measured axial spring rate = 516 lbf/in.

## Slide 10: Conclusions
All drawings (except drawings of pion donut support assembly) of CD-3a items were approved.
Prototype window was successfully tested up to 27.8 psi (> 125% of 22 psi) without plastic deformation.
Use of stainless steel 316L or 316LN for Bellows 1-4 will reduce cost and lower the risk.
Prototype Bellows 7 are received, tested and accepted.
Request of length change of SAM pipe was presented to Technical Review Board and approved by TRB. NX model and relevant drawings were updated.
CD-3a beampipes and bellows are in procurement stage

## Slide 11
Backup

## Slide 12: Beam Pipe from Target to Collar 0
Vacuum Equalization System
Beam Direction
Lead Casting
Adjustment and Support System
Cu Cooling Tube
Lead Containment Vessel
Cooling Tube Exit Jacket (2X)
Cross sectional View
Collar 0
Target
US enclosure
Collar 0
12’’ OD  0.25’’ wall aluminum tube
12’’ Bellows 1
12’’ Bellows 2
Bellows 1 and 2 are identical.
Collar 0’s lead is cast into the containment vessel.
Bore in Collar 0 is precisely machined to be perpendicular and concentric with the upstream flange of the assembly.
Status: drawings were reviewed and updated.
0.55’’ gap - target flange to bellows 1
Precision-Machined Bore

## Slide 13: SAM Pipe
OD = 16’’
Thick = 0.25’’
Thickness = 1.25’’
Slots for rotational adjustment
16’’ pipe
SAM pipe is to precisely mount the SAM detectors.
  Roughly machine round support bars;
  Weld round support bars to the 16’’ pipe;
  After welding, machine round support bars according tolerances;
  Weld 2.5’’ tubes to round support bars;
  Weld 4.5’’ bi-metal flange to tubes.
Status
  Final drawings reviewed and updated.
2.5’’ OD Tube
Atlas 4.5’’ Ti-Al CF flange
Round support bar
Pallowable (Div 2)
= 168 psi >> 14.7 psi
Min code required thickness = 1.16’’
SAM detector
Drawing:
A09005-15-06-2000

## Slide 14: Support of Beam Dump Entry Pipe (OD = 24’’, thickness = 3/16’’)
Fvacuum= 3536 lbf
Beam dump entry pipe is floating and needs restraint in Z to resist vacuum load from Bellows 7.
There is a 3536 lbf (Fz) vacuum force pointing upstream.
One Z link, two X links and three Y links are used to support the pipe.
Links are made of aluminum HEX BAR.
Fx1 = 428 lbf (compressive), critical buckling load of x link = 63,000 lbf.
Fx2 = 428 lbf (tensile).
Total weight = 716 lbf.
Status
  Final drawings are approved.
X
Y
Z
0.75’’ thick
3/16’’ thick
Z link
Y link
X link
Mount to existing ceiling unistruct
Anchor to wall
Fx2
Fx1
Drawing:
A09005-15-09-1009