## Sheet1
Activity ID | Activity Name | Start | Finish | BL Project Start | BL Project Finish
Upstream Toroid |  | 05-Apr-21 A | 2026-07-09 | 2020-12-16 | 2026-01-22
Upstream Toroid Coils |  | 05-Apr-21 A | 2026-07-09 | 2021-04-23 | 2026-01-22
1030301075 | Prepare US Toroid Assembly and Alignment Hardware Procurement Package | 19-Mar-25 A | 2025-11-26 | 2025-01-10 | 2025-02-21
1030301081 | TR Effort US Toroid Assembly and Alignment Hardware | 06-May-25 A | 2025-10-16 | 2025-03-20 | 2025-04-09
1030301086 | Additional Vendor effort US Toroid Assembly and Alignment Hardware - Rod Ends | 01-Jul-25 A | 2025-10-17 | 2025-05-06 | 2025-10-16
1030301091R | Inspect US Toroid Assembly and Alignment Hardware (Replan) | 2026-01-13 | 2026-02-03 | 2025-10-20 | 2025-11-07
1030301092 | ACCEPT: US Toroid Assembly and Alignment Hardware - Rod Ends | 2025-10-20 | 2025-10-20 | 2025-10-17 | 2025-10-17
1030301094 | SOW for US Toroid Integration and Interconnections Hardware | 2025-09-02 | 2025-09-03 | 2024-09-10 | 2024-09-11
1030301100 | Prepare US Toroid Integration and Interconnections Hardware Procurement Package | 2025-10-31 | 2025-11-13 | 2024-11-22 | 2025-01-09
1030301106 | TR Effort for US Toroid Integration and Interconnections Hardware | 2025-12-02 | 2026-01-14 | 2025-07-03 | 2025-08-07
1030301110 | Vendor Effort US Toroid Integration and Interconnections Hardware | 2025-12-02 | 2026-01-14 | 2025-07-03 | 2025-08-07
1030301115 | ACCEPT: US Toroid Integration and Interconnections Hardware | 2026-01-15 | 2026-01-15 | 2025-08-08 | 2025-08-08
1030301116 | Inspect US Toroid Integration and Interconnections Hardware | 2026-01-16 | 2026-01-20 | 2025-08-11 | 2025-08-12
1030301149 | SOW for US Toroid Coil Clamps and Support Links | 2025-09-02 | 2025-09-23 | 2024-09-10 | 2024-09-11
1030301155 | Prepare US Toroid Coil Clamps and Support Links Procurement Package | 2025-09-25 | 2025-10-29 | 2024-09-13 | 2024-10-17
1030301161 | TR Effort for US Toroid Coil Clamps and Support Links | 2025-10-31 | 2026-04-30 | 2024-10-21 | 2025-04-21
1030301165 | Vendor effort US Toroid Coil Clamps and Support Links | 2025-10-31 | 2026-04-30 | 2024-10-21 | 2025-04-21
10303011699 | SOW for US Coil Tungsten Side Plates | 2025-09-02 | 2025-09-15 | 2024-09-10 | 2024-09-11
1030301170 | ACCEPT: US Toroid Coil Clamps and Support Links | 2026-05-01 | 2026-05-01 | 2025-04-22 | 2025-04-22
1030301171 | Inspect US Toroid Coil Clamps and Support Links | 2026-05-04 | 2026-05-05 | 2025-04-23 | 2025-04-24
10303011710 | Prepare US Coil Tungsten Side Plates Procurement Package | 2025-09-17 | 2025-10-21 | 2024-09-13 | 2024-10-17
10303011721 | TR Effort for US Coil Tungsten Side Plates | 2025-10-23 | 2026-02-18 | 2024-10-21 | 2025-02-17
10303011730 | Vendor effort US Coil Tungsten Side Plates | 2025-10-23 | 2026-02-18 | 2024-10-21 | 2025-02-17
10303011740 | ACCEPT: US Coil Tungsten Side Plates | 2026-02-19 | 2026-02-19 | 2025-02-18 | 2025-02-18
103030117400 | Inspect, Prepare and Survey TM0 Coil 1 | 11-Aug-25 A | 2025-09-08 | 2024-11-18 | 2024-11-22
103030117405 | Machine TM0 Coil 1 - M&S | 2025-09-09 | 2025-09-16 | 2024-11-25 | 2024-12-04
10303011741 | Inspect US Coil Tungsten Side Plates | 2026-02-20 | 2026-02-23 | 2025-02-19 | 2025-02-20
103030117410 | Inspect, Prepare and Survey TM0 Coil 2 | 11-Aug-25 A | 2025-09-16 | 2024-11-25 | 2024-12-04
103030117415 | Machine TM0 Coil 2 - M&S | 2025-09-17 | 2025-09-23 | 2024-12-05 | 2024-12-11
103030117420 | Inspect, Prepare and Survey TM0 Coil 3 | 11-Aug-25 A | 2025-09-23 | 2024-12-05 | 2024-12-11
103030117425 | Machine TM0 Coil 3 - M&S | 2025-09-24 | 2025-09-30 | 2024-12-12 | 2024-12-18
103030117430 | Inspect, Prepare and Survey TM0 Coil 4 | 18-Aug-25 A | 2025-09-30 | 2024-12-12 | 2024-12-18
103030117435 | Machine TM0 Coil 4 - M&S | 2025-10-01 | 2025-10-07 | 2024-12-19 | 2025-01-06
103030117440 | Inspect, Prepare and Survey TM0 Coil 5 | 18-Aug-25 A | 2025-10-07 | 2024-12-19 | 2025-01-06
103030117445 | Machine TM0 Coil 5 - M&S | 2025-10-08 | 2025-10-14 | 2025-01-07 | 2025-01-13
103030117450 | Inspect, Prepare and Survey TM0 Coil 6 | 18-Aug-25 A | 2025-10-14 | 2025-01-07 | 2025-01-13
103030117455 | Machine TM0 Coil 6 - M&S | 2025-10-15 | 2025-10-21 | 2025-01-14 | 2025-01-21
103030117460 | Inspect, Prepare and Survey TM0 Coil 7 | 18-Aug-25 A | 2025-10-21 | 2025-01-14 | 2025-01-21
103030117465 | Machine TM0 Coil 7 - M&S | 2025-10-22 | 2025-10-28 | 2025-01-22 | 2025-01-28
103030117470 | Attach Coil Clamps to TM0 Coil 1 | 2026-05-06 | 2026-05-12 | 2025-11-10 | 2025-11-14
103030117475 | Machine Shop Support TM0 Coil 1 - M&S | 2026-05-13 | 2026-05-18 | 2025-11-17 | 2025-11-20
103030117485 | Attach Coil Clamps to TM0 Coil 2 | 2025-09-24 | 2025-09-30 | 2024-12-12 | 2024-12-18
103030117490 | Machine Shop Support TM0 Coil 2 - M&S | 2025-10-01 | 2025-10-06 | 2024-12-19 | 2025-01-03
103030117491 | SOW US Toroid Frame | 2025-09-02 | 2025-09-24 | 2024-09-12 | 2024-09-13
10303011750 | Install Tungsten Side Plates and Fiducialize TM0 Coil 1 Assembly | 2026-05-19 | 2026-05-26 | 2025-11-21 | 2025-12-01
103030117500 | Attach Coil Clamps to TM0 Coil 3 | 2025-10-01 | 2025-10-07 | 2024-12-19 | 2025-01-06
103030117505 | Machine Shop Support TM0 Coil 3 - M&S | 2025-10-08 | 2025-10-13 | 2025-01-07 | 2025-01-10
103030117515 | Attach Coil Clamps to TM0 Coil 4 | 2025-10-08 | 2025-10-14 | 2025-01-07 | 2025-01-13
103030117520 | Machine Shop Support TM0 Coil 4 - M&S | 2025-10-15 | 2025-10-20 | 2025-01-14 | 2025-01-17
103030117530 | Attach Coil Clamps to TM0 Coil 5 | 2025-10-15 | 2025-10-21 | 2025-01-14 | 2025-01-21
103030117535 | Machine Shop Support TM0 Coil 5 - M&S | 2025-10-22 | 2025-10-27 | 2025-01-22 | 2025-01-27
103030117545 | Attach Coil Clamps to TM0 Coil 6 | 2025-10-22 | 2025-10-28 | 2025-01-22 | 2025-01-28
10303011755 | Install Tungsten Side Plates and Fiducialize TM0 Coil 2 Assembly | 2026-05-27 | 2026-06-02 | 2025-12-02 | 2025-12-08
103030117550 | Machine Shop Ream holes and install pins TM0 Coil 6 - M&S | 2025-10-29 | 2025-11-03 | 2025-01-29 | 2025-02-03
103030117560 | Attach Coil Clamps to TM0 Coil 7 | 2025-10-29 | 2025-11-04 | 2025-01-29 | 2025-02-04
103030117565 | Machine Shop Support TM0 Coil 7 - M&S | 2025-11-05 | 2025-11-10 | 2025-02-05 | 2025-02-10
10303011760 | Install Tungsten Side Plates and Fiducialize TM0 Coil 3 Assembly | 2026-06-03 | 2026-06-09 | 2025-12-09 | 2025-12-15
10303011765 | Install Tungsten Side Plates and Fiducialize TM0 Coil 4 Assembly | 2026-06-10 | 2026-06-16 | 2025-12-16 | 2025-12-22
10303011770 | Install Tungsten Side Plates and Fiducialize TM0 Coil 5 Assembly | 2026-06-17 | 2026-06-24 | 2025-12-23 | 2026-01-07
10303011775 | Install Tungsten Side Plates and Fiducialize TM0 Coil 6 Assembly | 2026-06-25 | 2026-07-01 | 2026-01-08 | 2026-01-14
10303011780 | Install Tungsten Side Plates and Fiducialize TM0 Coil 7 Assembly | 2026-07-02 | 2026-07-09 | 2026-01-15 | 2026-01-22
1030301180 | Prepare US Toroid Frame Procurement Package | 2025-09-26 | 2025-10-30 | 2024-10-18 | 2024-11-21
1030301186 | TR Effort US Toroid Frame | 2025-11-04 | 2026-05-04 | 2025-02-13 | 2025-08-04
1030301190 | Vendor effort US Toroid Frame (TM0) | 2025-11-04 | 2026-05-04 | 2025-02-13 | 2025-08-04
1030301195 | ACCEPT: US Toroid Frame (TM0) | 2026-05-05 | 2026-05-05 | 2025-08-05 | 2025-08-05
1030301196 | Inspect US Toroid Frame | 2026-05-06 | 2026-05-19 | 2025-08-06 | 2025-08-07
1030301199 | SOW for US Toroid Water Headers and Feeders (TM0) | 2025-10-31 | 2025-11-13 | 2024-11-22 | 2024-12-09
1030301205 | Prepare US Toroid Water Headers and Feeders Procurement Package | 2025-11-17 | 2025-12-23 | 2024-12-11 | 2025-01-27
1030301211 | TR Effort for US Toroid Water Headers and Feeders (TM0) | 2026-01-05 | 2026-03-30 | 2025-01-29 | 2025-04-22
1030301215 | Vendor effort US Toroid Water Headers and Feeders (TM0) | 2026-01-05 | 2026-03-30 | 2025-01-29 | 2025-04-22
1030301220 | ACCEPT: US Toroid Water Headers and Feeders (TM0) | 2026-03-31 | 2026-03-31 | 2025-04-23 | 2025-04-23
1030301221 | Inspect US Toroid Water Headers and Feeders (TM0) | 2026-04-01 | 2026-04-02 | 2025-04-24 | 2025-04-25
1030301224 | SOW for US Toroid Electrical Busbars (TM0) | 2026-01-02 | 2026-01-05 | 2025-01-28 | 2025-01-29
1030301230 | Prepare US Toroid Electrical Busbars Procurement Package | 2026-01-07 | 2026-02-11 | 2025-01-31 | 2025-03-06
1030301236 | TR Effort for US Toroid Electrical Busbars (TM0) | 2026-02-13 | 2026-05-07 | 2025-03-10 | 2025-06-02
1030301240 | Vendor effort US Toroid Electrical Busbars (TM0) | 2026-02-13 | 2026-05-07 | 2025-03-10 | 2025-06-02
1030301245 | ACCEPT: US Toroid Electrical Busbars (TM0) | 2026-05-08 | 2026-05-08 | 2025-06-03 | 2025-06-03
1030301246 | Inspect US Toroid Electrical Busbars (TM0) | 2026-05-11 | 2026-05-12 | 2025-06-04 | 2025-06-05
103030520 | Vendor effort US Toroid Assembly and Alignment Hardware - Rod Bodies | 2025-10-07 | 2026-01-09 | 2025-07-08 | 2025-09-30
103030525 | ACCEPT: US Toroid Assembly and Alignment Hardware - Rod Bodies | 2026-01-12 | 2026-01-12 | 2025-10-01 | 2025-10-01
Upstream Toroid Enclosure |  | 17-Apr-21 A | 2026-06-18 | 2020-12-16 | 2026-01-02
1030302005SB | TR effort for Upstream Toroid Enclosure and ancillary hardware- Labor Post CD-2/3 Setting of Baseline | 2025-11-26 | 2026-05-27 | 2024-06-03 | 2024-11-20
1030302010SB | TR effort for Upstream Toroid Enclosure and ancillary hardware- M&S Post CD-2/3 Setting of Baseline | 2025-11-26 | 2026-05-27 | 2024-06-03 | 2024-11-20
1030302075 | Prepare US Toroid Enclosure supports Procurement Package | 2025-10-21 | 2025-11-24 | 2025-02-11 | 2025-03-17
1030302081 | TR Effort for US Toroid Enclosure supports | 2025-11-26 | 2026-03-31 | 2025-03-19 | 2025-07-11
1030302085 | Vendor effort US Toroid Enclosure supports | 2025-11-26 | 2026-03-31 | 2025-03-19 | 2025-07-11
1030302090 | ACCEPT: US Toroid Enclosure supports | 2026-04-01 | 2026-04-01 | 2025-07-14 | 2025-07-14
1030302091 | Inspect US Toroid Enclosure supports | 2026-04-02 | 2026-04-29 | 2025-07-15 | 2025-08-11
1030302106 | TR Effort for US Toroid Enclosure Electrical power penetrations | 01-Jul-25 A | 2025-09-15 | 2025-05-20 | 2025-06-10
1030302110 | Vendor effort US Toroid Enclosure Electrical power penetrations | 01-Jul-25 A | 2025-09-15 | 2025-04-28 | 2025-06-10
1030302115 | ACCEPT: US Toroid Enclosure Electrical power penetrations | 2025-09-16 | 2025-09-16 | 2025-06-11 | 2025-06-11
1030302116 | Inspect US Toroid Enclosure Electrical power penetrations | 2025-09-17 | 2025-09-18 | 2025-06-12 | 2025-06-13
1030302119 | SOW for US Toroid Enclosure Water penetrations | 23-Jan-25 A | 2025-09-22 | 2024-09-10 | 2024-09-11
1030302125 | Prepare US Toroid Enclosure Water penetrations Procurement Package | 2025-09-24 | 2025-10-28 | 2025-04-25 | 2025-05-30
1030302131 | TR Effort for US Toroid Enclosure Water penetrations | 2025-11-18 | 2025-11-19 | 2025-06-23 | 2025-06-24
1030302135 | Vendor effort US Toroid Enclosure Water penetrations sub Contract | 2025-10-30 | 2025-11-19 | 2025-06-03 | 2025-06-24
1030302140 | ACCEPT: US Toroid Water penetrations | 2025-11-20 | 2025-11-20 | 2025-06-25 | 2025-06-25
1030302141 | Inspect US Toroid Enclosure Water penetrations | 2025-11-21 | 2025-11-24 | 2025-06-26 | 2025-06-27
1030302150 | Prepare US Toroid Enclosure Procurement Package | 2025-09-16 | 2025-10-20 | 2025-01-06 | 2025-02-10
1030302156 | TR Effort for for US Toroid Enclosure | 2025-11-03 | 2026-06-15 | 2025-02-12 | 2025-09-15
1030302160 | Vendor effort US Toroid Enclosure | 2025-11-03 | 2026-06-15 | 2025-02-12 | 2025-09-15
1030302165 | ACCEPT: US Toroid Enclosure | 2026-06-16 | 2026-06-16 | 2025-09-16 | 2025-09-16
1030302166 | Inspect US Toroid Enclosure | 2026-06-17 | 2026-06-18 | 2025-09-17 | 2025-09-18
1030302411SB | Produce Rack layout drawings (Replan) | 02-Dec-24 A | 2025-09-15 | 2024-06-03 | 2024-07-03
1030302415SB | Design Cable routing and connection | 03-Mar-25 A | 2025-09-29 | 2024-07-05 | 2024-09-10
1030302420SB | Specify New electrical boards, circuit breakers | 09-Jun-25 A | 2025-10-02 | 2024-09-11 | 2024-09-17
1030302425SB | Produce Control and monitoring software | 09-Jun-25 A | 2025-10-09 | 2024-09-18 | 2024-10-08
1030302540 | Vendor effort MOLLER US Engineering Part II - Bartoszek - MOD 3 | 01-Aug-25 A | 2026-02-24 | 2025-07-10 | 2025-12-23
1030302545 | ACCEPT: MOLLER US Engineering Part II - Bartoszek - MOD 3 | 01-Aug-25 A | 2025-09-02 | 2026-01-02 | 2026-01-02
1030302555 | Vendor effort MOLLER US Engineering Part II - Bartoszek | 2025-09-09 | 2025-11-26 | 2025-10-02 | 2025-12-23
1030302560 | ACCEPT: MOLLER US Engineering Part II - Bartoszek | 2025-12-01 | 2025-12-01 | 2026-01-02 | 2026-01-02
Upstream Toroid Collimators |  | 01-Nov-21 A | 2026-03-02 | 2021-11-01 | 2026-01-05
1030303080SB | TR Effort for Collimators #1 and #2 - Labor | 01-May-25 A | 2025-09-16 | 2024-09-19 | 2025-03-20
1030303081 | TR Effort for Machining Collimators #1 and #2 - Labor | 2025-09-02 | 2025-10-30 | 2025-05-15 | 2025-09-29
1030303085SB | TR Travel for Collimators #1 and #2 - M&S | 2025-09-11 | 2025-12-12 | 2024-09-19 | 2025-03-20
1030303091 | Vendor effort Collimators #1 and #2 Brazing | 14-Apr-25 A | 2025-12-12 | 2025-04-14 | 2025-07-23
1030303093 | Vendor effort Collimators #1 and #2 Material and Machining | 02-Jun-25 A | 2025-10-01 | 2025-05-15 | 2025-09-29
1030303097 | ACCEPT: Collimators #1 and #2 Brazing | 2025-12-15 | 2025-12-15 | 2025-07-24 | 2025-07-24
1030303099 | ACCEPT: Collimators #1 and #2 Material and Machining | 2025-10-31 | 2025-10-31 | 2025-09-30 | 2025-09-30
1030303101 | Inspect Collimators #1 and #2 (Replan) | 2025-12-17 | 2025-12-18 | 2026-01-02 | 2026-01-05
1030303103 | Vendor effort Collimators #1 and #2 Brazing Consultants Mod 001 | 13-Aug-25 A | 2025-12-15 | 2025-10-02 | 2025-12-22
1030303104 | ACCEPT: Collimators #1 and #2 Brazing Consultants Mod 001 | 2025-12-16 | 2025-12-16 | 2025-12-23 | 2025-12-23
1030303499 | SOW for Lead Mini Wall | 30-Sep-25* | 2025-10-13 | 2024-09-10 | 2024-09-11
1030303505 | Prepare Lead Mini Wall Procurement Package | 2025-10-15 | 2025-11-18 | 2024-09-13 | 2024-10-17
1030303511 | TR Effort for Lead Mini Wall | 2025-11-20 | 2026-02-25 | 2024-10-21 | 2025-01-27
1030303515 | Vendor effort Lead Mini Wall | 2025-11-20 | 2026-02-25 | 2024-10-21 | 2025-01-27
1030303520 | ACCEPT: Lead Mini Wall | 2026-02-26 | 2026-02-26 | 2025-01-28 | 2025-01-28
1030303521 | Inspect Lead Mini Wall | 2026-02-27 | 2026-03-02 | 2025-01-29 | 2025-01-30
1030303524 | SOW for Shielding for O'ring | 30-Sep-25* | 2025-10-01 | 2024-09-10 | 2024-09-11
1030303530 | Prepare Shielding for O'ring Procurement Package | 2025-10-03 | 2025-10-23 | 2024-09-13 | 2024-10-03
1030303536 | TR Effort for Shielding for O'ring | 2025-10-27 | 2026-01-30 | 2024-10-07 | 2025-01-10
1030303540 | Vendor effort Shielding for O'ring | 2025-10-27 | 2026-01-30 | 2024-10-07 | 2025-01-10
1030303545 | ACCEPT: Shielding for O'ring | 2026-02-02 | 2026-02-02 | 2025-01-13 | 2025-01-13
1030303546 | Inspect Shielding for O'ring | 2026-02-03 | 2026-02-04 | 2025-01-14 | 2025-01-15
103030695 | TR Effort for US Toroid Contract for MIT Design Extension Effort | 06-Jun-24 A | 2025-12-23 | 2024-07-25 | 2024-07-31
103030805 | Vendor effort MIT Completion of US Engineering - MOD 8 | 07-May-25 A | 2025-12-23 | 2025-07-09 | 2025-12-23
103030810 | ACCEPT: MIT Completion of US Engineering - MOD 8 | 01-Aug-25 A | 2026-01-02 | 2026-01-02 | 2026-01-02
Spectrometer Assembly |  | 01-Feb-23 A | 2026-08-21 | 2022-05-03 | 2026-03-06
10306000 | Assemble and Test Electronics Racks and Cables | 2025-10-17 | 2025-11-13 | 2024-10-10 | 2024-11-06
10306001 | Conduct Toroid Magnet Assembly and Test Safety Review | 2025-11-20 | 2025-11-21 | 2025-05-30 | 2025-06-02
103060100 | Assemble frame for TM0 | 2026-05-20 | 2026-05-27 | 2025-08-08 | 2025-08-14
103060150 | Install Cooling Loop and Busbar on TM0 Frame | 2026-05-28 | 2026-05-29 | 2025-08-15 | 2025-08-18
103060190 | Install Cooling Loop and Busbar on TM4 Frame | 01-Oct-24 A | 2025-09-16 | 2024-10-04 | 2024-10-07
103060200 | Install, Survey and Align TM0 Coil 1 | 2026-06-01 | 2026-06-01 | 2025-12-02 | 2025-12-02
103060210 | Connect Cooling and Electrical to TM0 Coil 1 | 2026-06-02 | 2026-06-02 | 2025-12-03 | 2025-12-03
103060220 | Install, Survey and Align TM0 Coil 2 | 2026-06-03 | 2026-06-03 | 2025-12-04 | 2025-12-04
103060230 | Connect Cooling and Electrical to TM0 Coil 2 | 2026-06-04 | 2026-06-04 | 2025-12-09 | 2025-12-09
103060240 | Install, Survey and Align TM0 Coil 3 | 2026-06-05 | 2026-06-05 | 2025-12-10 | 2025-12-10
103060250 | Connect Cooling and Electrical to TM0 Coil 3 | 2026-06-10 | 2026-06-10 | 2025-12-16 | 2025-12-16
103060260 | Install, Survey and Align TM0 Coil 4 | 2026-06-11 | 2026-06-11 | 2025-12-17 | 2025-12-17
103060270 | Connect Cooling and Electrical to TM0 Coil 4 | 2026-06-17 | 2026-06-17 | 2025-12-23 | 2025-12-23
103060280 | Install, Survey and Align TM0 Coil 5 | 2026-06-18 | 2026-06-18 | 2026-01-02 | 2026-01-02
103060290 | Connect Cooling and Electrical to TM0 Coil 5 | 2026-06-25 | 2026-06-25 | 2026-01-08 | 2026-01-08
103060300 | Install, Survey and Align TM0 Coil 6 | 2026-06-26 | 2026-06-26 | 2026-01-09 | 2026-01-09
103060310 | Connect Cooling and Electrical to TM0 Coil 6 | 2026-07-02 | 2026-07-02 | 2026-01-15 | 2026-01-15
103060320 | Install, Survey and Align TM0 Coil 7 | 2026-07-06 | 2026-07-06 | 2026-01-16 | 2026-01-16
103060330 | Connect Cooling and Electrical to TM0 Coil 7 | 2026-07-10 | 2026-07-10 | 2026-01-23 | 2026-01-23
103060340 | Mount TM0 to US Enclosure Baseplate | 2026-07-13 | 2026-07-13 | 2026-01-26 | 2026-01-26
103060350 | Install Instrumentation on TM0 | 2026-07-13 | 2026-07-17 | 2026-01-26 | 2026-01-30
103060360 | TM0 - Connect Water Lines and Leak Check | 2026-07-20 | 2026-07-24 | 2026-02-02 | 2026-02-06
103060370 | TM0 - Route and insulate power bus bars and connection | 2026-07-27 | 2026-07-31 | 2026-02-09 | 2026-02-13
103060380 | TM0 - Check all electrical connections | 2026-08-03 | 2026-08-07 | 2026-02-16 | 2026-02-20
103060390 | TM0 - Survey and Align Coils | 2026-08-10 | 2026-08-12 | 2026-02-23 | 2026-02-25
103060400 | TM0 - Field Map and Adjust Coils | 2026-08-13 | 2026-08-13 | 2026-02-26 | 2026-02-26
103060441 | Assemble and Instrument Collimator 4 (Replan) | 2026-06-22 | 2026-06-26 | 2024-09-03 | 2024-09-09
10306310 | US Toroid - Assemble, Test Toroid Enclosure | 2026-06-29 | 2026-07-10 | 2025-09-19 | 2025-10-01
10306337 | US - Assemble and instrument collimators 1 and 2 (Replan) | 2025-12-19 | 2026-01-05 | 2026-01-06 | 2026-01-12
10306375 | US - Assemble and align collimators 1 and 2 to each other and to US Toroid | 2026-07-20 | 2026-07-24 | 2026-02-02 | 2026-02-06
10306400 | US - ASME pressure equipment testing and documentation | 2026-07-27 | 2026-07-31 | 2026-02-09 | 2026-02-13
10306405 | US - Install Enclosure top cover | 2026-08-14 | 2026-08-20 | 2026-02-27 | 2026-03-05
10306475 | US - Prep for Transport to Hall | 2026-08-21 | 2026-08-21 | 2026-03-06 | 2026-03-06